## Description
Design document: | https://docs.google.com/document/d/1wZsXl8XMl21V3WNjHIGPi_brwDXqoCBx7Pxdo1Abudo/edit#
Jira project: | P2 next gen (PP)
Jira label: | P2_v3
Number of tasks: | 78
Number of reported bugs: | 0
Total planned development worktime [h]: | 622
Planned development worktime of finished tasks [h]: | 271
Current worktime spent [h]: | 174.25
Planned time to finish project [h]: | 351
Project completeness based on planned worktime [%]: | 43.5691
Current worktime vs planned worktime [%]: | 64.2989 | > 100% - delay; < 100% - ahead

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | AWS Lambda | see design | [11 empty] | PP-328 |  |  |  | 0
1.1 | Set up the empty o2-grouper-lambda project | prepare the dev / qa / release branches, use p2-backend-v3 as template |  | 6 | 0.5 | 1 | 1 | Adrian Z. | March 5, 2021, 10:52 AM | March 5, 2021, 11:24 AM | 0.5 | 721 | 1 | PP-329 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | 1
1.2 | Create AWS lambda o2-grouper function | dev / qa / release versions |  | 3 | 3 | 4 | 4 | Adrian Z. | March 5, 2021, 11:30 AM | March 5, 2021, 4:14 PM | 5 | 9 | 0 | PP-330 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/1 | Sprint 2 |  | 4
1.3 | Create the API o2-grouper endpoints | dev / qa / release versions | 1.2 | 4 | 4 | 4 | 4 | Adrian Z. | March 8, 2021, 12:16 PM | March 8, 2021, 1:16 PM | 1 |  |  | PP-331 | - | Sprint 2 | No any commits - setup of AWS. | 4
1.4 | Set up the CI/CD pipeline | deploy to AWS lambda | 1.1 - 1.2 | 6 | 8 | 8 | 8 | Adrian Z. | March 5, 2021, 4:47 PM | March 9, 2021, 2:34 PM | 15 | 35 | 8 | PP-332 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/5 | Sprint 2 |  | 8
1.5 | Implement configuration validation |  | 1.4 | 4 | 4 | 6 | 6 | Adrian Z. | March 16, 2021, 11:19 AM | March 16, 2021, 4:53 PM | 5.5 | 360 | 1 | PP-333 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/10 | Sprint 2 |  | 6
1.6 | Implement creation of pipeline description object | create from validated configuration | 1.5, 1.9 | 3 | 4 | 4 | 4 | Adrian Z. | March 18, 2021, 10:22 AM | March 18, 2021, 12:34 PM | 2 | 109 | 1 | PP-334 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/12 | Sprint 2 |  | 4
1.7 | Register new pipeline in the database (or find existing) |  | 1.6, 2.1, 3 | 3 | 3 | 2 | 2 | [6 empty] | PP-335 |  | Sprint 8 |  | 0
1.8 | Initiatie the pyspark job (databricks) |  | 1.7, 3.2 | 8 | 8 | 12 | 12 | Adrian Z. | March 15, 2021, 9:47 AM | March 16, 2021, 10:20 AM | 9 | 77 | 5 | PP-336 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/9 | Sprint 2 |  | 12
1.9 | Auth token validation | extract user_id from token | 1.4 | 6 | 4 | 2 | 2 | Adrian Z. | March 16, 2021, 3:59 PM | March 17, 2021, 10:11 PM | 4 | 138 | 1 | PP-337 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/11 | Sprint 2 |  | 2
1.10 | Protect AWS lambda | needs to validate AWS access key before launching |  | 8 | 8 |  | 8 | Adrian Z. | April 12, 2021, 12:57 PM | April 13, 2021, 4:48 PM | 12.25 |  |  | PP-935 | - | Sprint 4 | Added to sprint in Sprint 4 | 8
1.11 | AWS Lambda configuration | allow passing configuration and user token to initiate a pipeline |  | 8 | 6 |  | 8 | Adrian Z. | April 9, 2021, 11:36 AM | April 12, 2021, 12:56 PM | 5.25 | 51.5 | 11 | PP-936 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/13 | Sprint 4 | Added to sprint in Sprint 4 | 8
1.12 | AWS Lambda error handling | format error response objects |  | 6 | 3 |  | 6 | Adrian Z. | April 12, 2021, 12:57 PM | April 12, 2021, 12:08 PM | 2.75 | 51.5 | 11 | PP-937 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/merge_requests/13 | Sprint 4 | Added to sprint in Sprint 4 | 6
2 | Pipeline Database | [12 empty] | PP-338 |  |  |  | 0
2.1 | Set up dev / qa / release databases (postgres/aurora) | can use existing instances, create public schema for pipelines |  | 4 | 4 | 4 | 4 | Adrian Z. | [5 empty] | PP-339 |  | Sprint 8 |  | 0
3 | O2 Grouper Job | [12 empty] | PP-340 |  |  |  | 0
3.1 | Set up the empty o2-grouper-job project in python |  |  | 4 | 0.5 | 1 | 1 | Adrian Z. | March 5, 2021, 10:51 AM | March 5, 2021, 11:23 AM | 0.5 | 721 | 1 | PP-341 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | 1
3.2 | Prepare the CI/CD pipelines for the o2-grouper-job project | Must be deployed to databricks | 3.1 | 16 | 16 | 20 | 20 | Adrian Z. | March 9, 2021, 3:22 PM | March 11, 2021, 9:15 AM | 14 | 30 | 1 | PP-342 | https://gitlab-01.itx.pl/p2-project/o2-grouper-lambda/-/commit/6e6f779574b800e2cd18cf806f01585869a33c88 | Sprint 2 |  | 20
3.3 | Repository | see design | [11 empty] | PP-343 |  |  |  | 0
3.3.1 | Define AbstractRepository and implement MockRepository (in-memory) | only implement the methods: add_pipeline, add_artifact, find_artifact in the MockRepository |  | 10 | 12 | 16 | 16 | Adrian Z. | March 19, 2021, 10:07 AM | March 22, 2021, 11:15 AM | 8 | 198 | 5 | PP-344 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/4 | Sprint 3 | Sprint 2 and Sprint 3 | 16
3.3.5 | Read o2-grouper.config file | see design |  | 2 | 1 | 1 | 1 | Adrian Z. | March 22, 2021, 11:14 AM | March 22, 2021, 12:00 PM | 1 | 60 | 0 | PP-412 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/5 | Sprint 3 |  | 1
3.3.2 | Implent PipelineRepository | use postgres database connector, use SQLAlchemy for implementation of queries, only implement the methods: add_pipeline, add_artifact, find_artifact |  | 12 | 12 | 16 | 16 | Adrian Z. | March 22, 2021, 12:00 PM | March 24, 2021, 10:19 AM | 14 | 257 | 5 | PP-413 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/6 | Sprint 3 |  | 16
3.3.3 | Define AbstractFileSystem and implement MockFileSystem (for tests) | see design |  | 6 | 8 | 8 | 8 | Adrian Z. | March 24, 2021, 9:23 AM | March 24, 2021, 12:45 PM | 3 | 160 | 2 | PP-414 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/7 | Sprint 3 |  | 8
3.3.4 | Implement DBFS class implementing AbstractFileSystem interface | see design |  | 8 | 16 | 16 | 16 | Adrian Z. | March 24, 2021, 12:46 PM | March 25, 2021, 10:00 AM | 5 | 114 | 31 | PP-415 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/8 | Sprint 3 | Spent some time for help for Manoj ~7h | 16
3.4 | Dataset schema recognition | see design | [11 empty] | PP-345 |  |  |  | 0
3.4.1 | Implement detect_schema method |  | 3.2, 3.3 | 3 | 3 | 4 | 4 | Adrian Z. | March 25, 2021, 10:01 AM | March 25, 2021, 4:12 PM | 3 | 88.5 | 0 | PP-346 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/9 | Sprint 3 |  | 4
3.4.2 | Implement resolve_dataset_id method |  | 3.2, 3.3 | 4 | 4 | 4 | 4 | Adrian Z. | March 25, 2021, 10:36 AM | March 25, 2021, 4:12 PM | 3 | 88.5 | 0 | PP-347 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/9 | Sprint 3 |  | 4
3.4.3 | Implement get_dataset_schema method |  | 3.4.1, 3.4.2 | 5 | 4 | 8 | 8 | Adrian Z. | March 25, 2021, 4:18 PM | March 29, 2021, 12:00 PM | 12 | 261 | 29 | PP-348 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/10 | Sprint 3 |  | 8
3.5 | LDS dataset validation | see design | [11 empty] | PP-349 |  |  |  | 0
3.5.1 | Implement get_claim_file_type method |  |  | 3 | 3 | 2 | 2 | Adrian Z. | March 29, 2021, 12:04 PM | March 29, 2021, 1:54 PM | 2 | 77 | 1.5 | PP-350 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/11 | Sprint 3 |  | 2
3.5.2 | Implement find_fts_file method |  |  | 3.5 | 2 | 2 | 2 | Adrian Z. | March 29, 2021, 1:55 PM | March 29, 2021, 5:04 PM | 2 | 77 | 1.5 | PP-351 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/11 | Sprint 3 |  | 2
3.5.3 | Implement read_fts method |  |  | 5.5 | 8 | 8 | 8 | Adrian Z. | March 30, 2021, 10:03 AM | March 30, 2021, 2:36 PM | 4.5 | 82 | 1 | PP-352 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/12 | Sprint 3 |  | 8
3.5.4 | Implement read_claims_file method |  |  | 3.5 | 4 | 4 | 4 | Adrian Z. | March 30, 2021, 2:37 PM | March 30, 2021, 4:31 PM | 2 | 62 | 9 | PP-353 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/13 | Sprint 3 | Added to sprint 3 | 4
3.5.5 | Implement LDSDataset class |  | 3.5.1 - 3.5.4 | 6.5 | 8 | 10 | 10 | Adrian Z. | March 30, 2021, 4:43 PM | April 1, 2021, 9:46 AM | 10 | 276 | 37 | PP-354 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/14 | Sprint 3 | Added to sprint 3 | 10
3.6 | P2 dataset validation | see design | [11 empty] | PP-355 |  |  |  | 0
3.6.1 | Adapt validation code from the existing project | use pandas for validation, drop invalid lines, store validation statistics | 3.3.1 | 24 | 32 | 32 | 32 | Adrian Z. | April 1, 2021, 9:47 AM | April 6, 2021, 12:02 PM | 13.25 | 705 | 3 | PP-416 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/15 | Sprint 4 |  | 32
3.6.2 | Implement P2UploadDataset | implement all methods |  | 18 | 20 | 24 | 24 | Adrian Z. | April 6, 2021, 12:10 PM | April 7, 2021, 12:00 PM | 5 | 143.5 | 16 | PP-417 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/16 | Sprint 4 |  | 24
3.6.3 | Implement import_as_parquet method | see design |  | 16 | 16 | 16 | 16 | Adrian Z. | April 7, 2021, 12:00 PM | April 8, 2021, 10:01 AM | 6.25 | 72 | 4 | PP-418 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/17 | Sprint 4 | ? | 16
3.6.4 | Implement pipeline steps: schema recognition, validation, import and integrate with the pipeline | Integrate already implemented functions and classes | 3.4, 3.5, 3.6.1 | 24 | 32 | 40 | 40 | Adrian Z. | April 8, 2021, 10:03 AM |  |  |  |  | PP-419 |  | Sprint 5 |  | 0
3.6.5 | Collect and report validation statistics | see also pipeline statistics | 3.6.4, 4.6 | 8 | 8 | 16 | 16 | Adrian Z. | April 6, 2021, 4:11 PM | April 7, 2021, 11:59 AM | 3.5 | 143.5 | 16 | PP-420 | https://gitlab-01.itx.pl/p2-project/o2-grouper-job/-/merge_requests/16 | Sprint 4 |  | 16
3.7 | Stay Maker 1 (CMS) | see design | [11 empty] | PP-421 |  |  | Low priority | 0
3.7.1 | Implement make_lds_stays | use the existing scala implementation | 3.2, 3.3.2 | 40 | 40 | 40 | 40 | [6 empty] | PP-422 |  |  | Removed from sprint 3 | 0
3.7.2 | Integrate stay maker 1 with the pipeline |  | 3.7.1 | 4 | 8 | 8 | 4 | [6 empty] | PP-423 |  |  |  | 0
3.8 | Stay Maker 2 (P2 Upload) | see design | [11 empty] | PP-424 |  |  |  | 0
3.8.1 | Implement make_p2_stays method |  |  | 32 | 40 | 40 | 32 | [6 empty] | PP-425 |  | Sprint 5 |  | 0
3.8.2 | Integrate stay maker 2 with the pipeline |  |  | 4 | 8 | 8 | 4 | [6 empty] | PP-426 |  | Sprint 6 |  | 0
3.8.3 | Collect and report stay maker's statistics | see design | 3.8.2, 4.6 | 8 | 8 | 8 | 8 | [6 empty] | PP-427 |  | Sprint 6 |  | 0
3.9 | Episode Maker | [12 empty] | PP-428 |  |  |  | 0
3.9.1 | Implement get_anchor_drgs in PipelineRepository |  | 3.3.2 | 6 | 4 | 4 | 6 | [6 empty] | PP-429 |  | Sprint 6 |  | 0
3.9.2 | Implement get_excluded_drgs in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | 3 | [6 empty] | PP-430 |  | Sprint 6 |  | 0
3.9.3 | Implement get_excluded_icds in PipelineRepository |  | 3.3.2 | 3 | 4 | 4 | 3 | [6 empty] | PP-431 |  | Sprint 6 |  | 0
3.9.4 | Implement make_episodes method | use the existing scala implementation | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | 32 | [6 empty] | PP-432 |  | Sprint 6 |  | 0
3.9.5 | Integrate episode maker with the pipeline |  | 3.9.4 | 4 | 8 | 8 | 4 | [6 empty] | PP-433 |  | Sprint 6 |  | 0
3.9.6 | Collect and report the episode maker's statistics |  | 3.9.5, 4.6 | 8 | 8 | 8 | 8 | [6 empty] | PP-434 |  | Sprint 6 |  | 0
3.10 | Relation Maker | see design | [11 empty] | PP-435 |  |  |  | 0
3.10.1 | Implement get_valid_entities method in PipelineRepository | fetch data generated by the "Entities PIpeline", return only the NPI number column | 3.3.2 | 10 | 4 | 2 | 10 | [6 empty] | PP-436 |  | Sprint 7 |  | 0
3.10.2 | Implement make_relations method | translate and refactor the scala code | 3.9.1 - 3.9.3, 3.2, 3.3.2 | 32 | 40 | 40 | 32 | [6 empty] | PP-437 |  | Sprint 7 |  | 0
3.10.3 | Integrate relation maker with the pipeline |  | 3.10.2 | 4 | 8 | 8 | 4 | [6 empty] | PP-438 |  | Sprint 7 |  | 0
3.10.4 | Collect and report the relation maker's statistics |  | 3.10.2, 4.6 | 6 | 8 | 8 | 6 | [6 empty] | PP-439 |  | Sprint 7 |  | 0
4 | Pipeline Logs & Status Reporting | see design | [11 empty] | PP-440 |  |  |  | 0
4.1 | Implement add_log method in PipelineRepository |  | 3.3.2 | 2 | 2 | 4 | 2 | [6 empty] | PP-441 |  | Sprint 7 |  | 0
4.2 | Add global error handler, log errorr |  | 3.2 | 2 | 2 | 4 | 2 | [6 empty] | PP-442 |  | Sprint 7 |  | 0
4.3 | Implemet set_status method in PipelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | 1.5 | [6 empty] | PP-443 |  | Sprint 7 |  | 0
4.4 | Implement set_stage method in PIpelineRepository |  | 3.3.2 | 1.5 | 2 | 4 | 1.5 | [6 empty] | PP-444 |  | Sprint 7 |  | 0
4.5 | Set status and stage during pipeline execution |  | 3.6 - 3.9 | 2 | 2 | 4 | 2 | [6 empty] | PP-445 |  | Sprint 7 |  | 0
4.6 | Implement the update_statistics method in PipelineRepository |  | 3.3.2 | 16 | 16 | 12 | 16 | [6 empty] | PP-446 |  | Sprint 7 |  | 0
5 | Dataset publishing and pipelne control | [12 empty] | PP-447 |  |  |  | 0
5.1 | Implement publish_relations_dataset method |  | DM, 3.3 | 24 | 28 | 32 | 24 | [6 empty] | PP-448 |  | Sprint 8 |  | 0
5.2 | Handle the pipeline_id control parameter |  | 1 - 3 | 3 | 3 | 3 | 3 | [6 empty] | PP-449 |  | Sprint 8 |  | 0
5.3 | Handle the template_pipeline_id parameter |  | 1 - 3 | 6.5 | 8 | 8 | 6.5 | [6 empty] | PP-450 |  | Sprint 8 |  | 0
5.4 | Handle start_from / stop_at parameters |  | 1 - 3 | 8 | 8 | 8 | 8 | [6 empty] | PP-451 |  | Sprint 8 |  | 0
5.5 | Implement published variables validation | integrate with the configuration validation (see design) | 1 | 3 |  | 4 | 3 | [6 empty] | PP-535 |  | Sprint 8 |  | 0
5.6 | Fill in published variable values | process publish_to JSON object | 5.5 | 3.5 |  | 4 | 3.5 | [6 empty] | PP-536 |  | Sprint 8 |  | 0
6 | Pipeline Server | see design | [11 empty] | PP-1009 |  |  |  | 0
6.1 | New project set-up | set up python project based on a template |  | 2 |  | 1 | 2 | [6 empty] | PP-1010 |  |  |  | 0
6.2 | Set up CI/CD pipelines | configure test, build and deployment pipelines |  | 6 |  | 4 | 6 | [6 empty] | PP-1011 |  |  |  | 0
6.3 | Implement AppConfig | validate configuration variables, see design |  | 4 |  | 4 | 4 | [6 empty] | PP-1012 |  |  |  | 0
6.4 | Implement getPipeline endpoint | integrate with Graphene, set up flask server, implement data model based on SQLAlchemy |  | 24 |  | 24 | 24 | [6 empty] | PP-1013 |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0