## Description
Design document: | Preferred Partners Backend v3
Jira project: | P2 next gen (PP)
Jira label: | P2_v3
Number of tasks: | 260
Number of reported bugs: | 5
Total planned development worktime [h]: | 1979
Planned development worktime of finished tasks [h]: | 1080.5
Current worktime spent [h]: | 1014.39
Planned time to finish project [h]: | 898.5
Project completeness based on planned worktime [%]: | 54.5983
Current worktime vs planned worktime [%]: | 93.8815 | > 100% - delay; < 100% - ahead

## Tasks
WBS | Name | Description | Depends on | Estimated development time [h] |  |  |  | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Sprint | Comment | Planned dates
|  |  |  | Designer | Reviewer | PM | Final |  | Start time | Finish time | Duration [h] | Insertions | Deletions |  |  |  |  | Start | Finish
1 | Analytical API | [12 empty] | PP-226 | [5 empty] | 0
1.1 | caseSummaryCollection endpoint | This is the basic functionality with filtering but without: benchmarks, pagination or sorting, some response elements are not present in the outputs | [11 empty] | PP-247 | [5 empty] | 0
1.1.1 | Implement Filter and derived classes - ColumnFilter, DistanceFilter |  |  | 3 | 4 | 4 | 4 | Michał | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 8 | 570 | 0 | PP-227 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/2 | Sprint 1 | More time due to code analysis tool rejections. | February 22, 2021, 5:13 PM | February 23, 2021, 12:08 PM | 4
1.1.2 | Implement extract_filters for the CaseSummaryFilterInputType input |  | 1.1.1 | 16 | 20 | 24 | 24 | Maciej | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 32 | 391 | 1 | PP-228 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 |  | February 23, 2021, 2:11 PM | March 1, 2021, 6:13 PM | 24
1.1.3 | Implement extract_filters for the CaseSummaryActionsInputType input |  | 1.1.1 | 4 | 4 | 6 | 6 | Aleksandra | March 4, 2021, 1:38 PM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-229 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 |  | March 4, 2021, 1:38 PM | March 11, 2021, 11:56 AM | 6
1.1.4 | Implement extract_filters for the RangeInputType input |  | 1.1.1 | 2 | 2 | 4 | 4 | Maciej | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4 | 391 | 1 | PP-230 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/8 | Sprint 1 |  | March 1, 2021, 12:13 PM | March 1, 2021, 6:13 PM | 4
1.1.5 | Implement filter_by method for pandas.DataFrame with the ColumnFilter |  | 1.1.1 | 4 | 4 | 6 | 6 | Michał | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 7 | 86 | 18 | PP-231 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/6 | Sprint 1 | More time due to code review rejection. | February 25, 2021, 5:46 PM | February 26, 2021, 4:25 PM | 6
1.1.6 | Implement filter_by method for pandas.DataFrame with the DistanceFilter |  | 1.1.1 | 12 | 16 | 16 | 16 | Michał | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 10 | 69 | 23 | PP-232 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/7 | Sprint 1 |  | February 26, 2021, 3:08 PM | March 1, 2021, 5:48 PM | 16
1.1.19 | Implement filter_by method for pandas.DataFrame with the RangeFilter |  | 1.1.1 | 2 |  | 4 | 4 | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 | PP-307 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 4
1.1.7 | Implement Node, NodeTypeEnum and NodeSubTypeEnum classes, implement get_node_type_from_subtype method |  |  | 3 | 4 | 6 | 6 | Maciej | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 3 | 98 | 0 | PP-233 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/3 | Sprint 1 | Forgot to change jira status at the beginning of the work on task. | February 23, 2021, 1:06 PM | February 23, 2021, 1:42 PM | 6
1.1.8 | Implement PandasProvider class (extending the AnalyticsProvider) | We should be able to pull data from files (available in the project) and join with entities_ac / entities_pac automatically / carelines |  | 8 | 12 | 16 | 16 | Michał | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 19 | 130 | 0 | PP-234 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/4 | Sprint 1 | More time spend due to fixes after code review + code fixes after more rigorous code analysis tool was implemented. | February 23, 2021, 12:12 PM | February 25, 2021, 3:43 PM | 16
1.1.20 | Add computed column fiscal_date to PandasAnalyticalService | fiscal_date = fiscal_year * 10 + fiscal_quarter |  | 2 |  | 4 | 4 | Maciej | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 2.5 | 77 | 13 | PP-308 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/11 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | March 2, 2021, 12:21 PM | March 2, 2021, 5:02 PM | 4
1.1.9 | Implement the PandasAnalyticalService find_nodes method | leave other methods unimplemented, all types of nodes should be supported | 1.1.8, 1.1.5, 1.1.6 | 16 | 20 | 24 | 24 | Michał | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 16 | 120 | 6 | PP-235 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/13 | Sprint 1 |  | March 2, 2021, 10:32 AM | March 3, 2021, 05:45 PM | 24
1.1.10 | Implement AbstractGraphQuery class and make_abstract_graph_query method | for now only implement the methods get_nodes and get_filters, leave the others unimplemented | 1.1.1 - 1.1.9 | 3 | 4 | 4 | 4 | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-236 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1 | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 4
1.1.11 | Implement AbstractGraphModel class and the make_abstract_graph_model method | for now do not handle the sorting or pagination info | 1.1.10 | 3 | 4 | 4 | 4 | Aleksandra | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 15 | 301 | 181 | PP-237 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/19 | Sprint 2 | postponed from Sprint 1 | March 9, 2021, 10:32 AM | March 11, 2021, 11:56 AM | 4
1.1.12 | Implement PandasAnalyticalService group_nodes method | All types of nodes should be supported | 1.1.8 | 32 | 40 | 48 | 48 | Maciej | March 4, 2021, 4:01 PM | March 16, 2021, 11:26PM | 64 | 707 | 345 | PP-238 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/29 | Sprint 2 | postponed from Sprint 1; finish delayed due to bug #1 | March 4, 2021, 4:01 PM | March 16, 2021, 11:26PM | 48
1.1.13 | Implement SummaryStatistics class and extract_node_statistics method | All types of nodes should be supported | 1.1.12 | 18 | 24 | 24 | 24 | Maciej | March 16, 2021, 12:04 PM | March 18, 2021, 1:43 PM | 18 | 347 | 7 | PP-239 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/49 | Sprint 2 | postponed from Sprint 1 | March 16, 2021, 12:04 PM | March 18, 2021, 1:43 PM | 24
1.1.14 | Implement extract_relation_statistics method | For now do not extract benchmark_value | 1.1.13 | 5 | 8 | 8 | 8 | Maciej | March 19, 2021, 11:34 AM | March 19, 2021, 4:26 PM | 5 | 195 | 46 | PP-240 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/57 | Sprint 2 |  | March 19, 2021, 11:34 AM | March 19, 2021, 4:26 PM | 8
1.1.15 | Implement PandasAnalyticalService get_entity_details method | Just pull matching data from entities data frames | 1.1.9 | 4 | 4 | 4 | 4 | Michał | March 8, 2021, 2:48 PM | March 9, 2021, 1:42 PM | 8 | 63 | 11 | PP-241 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/16 | Sprint 2 |  | March 8, 2021, 2:48 PM | March 9, 2021, 1:42 PM | 4
1.1.16 | Implement copy_summary_statistics method |  | 1.1.13 | 4 | 4 | 4 | 4 | Aleksandra | March 18, 2021, 5:55 PM | March 19, 2021, 12:55 PM | 4 | 530 | 0 | PP-242 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/54 | Sprint 2 |  | March 18, 2021, 5:55 PM | March 19, 2021, 12:55 PM | 4
1.1.24 | Implement copy_node_details method |  |  | 4 |  | 4 | 4 | Maciej | March 24, 2021, 9:21 AM | March 25, 2021, 3:55 PM | 10 | 152 | 22 | PP-502 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/75 | Sprint 3 | Added to sprint in Sprint 3 | March 24, 2021, 9:21 AM | March 25, 2021, 3:55 PM | 4
1.1.17 | Implement CaseSummaryQueryRunner class | For now ignore the groupingInfo, benchmarkValues, count and legendData responses, ignore benchmark Future argument | 1.1.1 - 1.1.16, 1.1.24, 1.1.25 | 28 | 32 | 32 | 32 | Maciej | March 22, 2021, 9:50 AM | March 31, 2021, 4:17 PM | 40 | 533 | 48 | PP-243 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/96 | Sprint 3 | postponed from Sprint 2 | March 22, 2021, 9:50 AM | March 31, 2021, 4:17 PM | 32
1.1.25 | Implement format_case_summary_element method |  |  | 4 |  | 4 | 4 | Maciej | March 30, 2021, 2:39 PM | March 30, 2021, 4:39 PM | 2 | 69 | 3 | PP-575 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/93 | Sprint 3 | Added to sprint in Sprint 3 | March 30, 2021, 2:39 PM | March 30, 2021, 4:39 PM | 4
1.1.18 | implement caseSummaryCollection endpoint |  | 1.1.17 | 4 | 4 | 4 | 4 | Maciej | April 1, 2021, 6:06 AM | April 1, 2021, 2:40 PM | 7.75 | 85 | 25 | PP-244 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/103 | Sprint 3 | Sprint 3 due to dependencies | April 1, 2021, 6:06 AM | April 1, 2021, 2:40 PM | 4
1.1.21 | Implement get_sql_filter for Node | should return python object | 1.1.7 | 5 |  | 8 | 8 | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 72 | 6 | PP-309 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 8
1.1.22 | Implement get_sql_group_column for Node | should return python object | 1.1.7 | 4 |  | 6 | 6 | Maciej | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 4 | 73 | 7 | PP-310 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/14 | Sprint 1 | Added to sprint - it appeard as a blocker for dependent tasks. | March 3, 2021, 4:58 PM | March 4, 2021, 1:39 PM | 6
1.1.23 | Implement get_sql_chilld_id column for Node |  | 1.1.7 | 4 |  | 4 | 4 | Maciej | March 9, 2021, 12:41 PM | March 9, 2021, 12:58 PM | 1 | 51 | 1 | PP-368 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/15 | Sprint 2 |  | March 9, 2021, 12:41 PM | March 9, 2021, 12:58 PM | 4
1.1.26 | groupingInfo in caseSummaryCollection result | [12 empty] | PP-1014
1.1.26.1 | Implement get_grouping_info method | see design |  | 5 |  |  | 5 | Tomek We | [5 empty] | PP-1007 |  | Sprint 4 | Added to sprint in sprint 4
1.1.26.2 | Handle grouping_info argument in copy_node_details, pass grouping_info when calling this method | run get_grouping_info and then use the results | 1.1.26.1 | 3.5 |  |  | 3.5 | Tomek We | [5 empty] | PP-1008 |  | Sprint 4 | Added to sprint in sprint 4
1.1.27 | auto-expanding of nodes | [12 empty] | PP-1015
1.2 | caseLocationDetails endpoint | For now we ignore the "state" output which is likely not used |  |  |  |  | 0 | [6 empty] | PP-248 | [5 empty] | 0
1.2.1 | implement extract_filters method | The method takes CaseLocationOptionInputType as input, use already existing extract_filters method implementation for the nested types | 1.1.2 - 1.1.4 | 6 | 8 | 8 | 8 | Michał | March 17, 2021, 1:56 PM | March 17, 2021, 6:32 PM | 7 | 171 | 21 | PP-249 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/46 | Sprint 2 |  | March 17, 2021, 1:56 PM | March 17, 2021, 6:32 PM | 8
1.2.2 | implement get_entity_counts method in PandasAnalyticalService | use data frames provided in the examples, calculate statistics both for PACs and hospitals | 1.1.8, 1.2.1 | 20 | 24 | 24 | 24 | Michał | March 9, 2021, 4:58 PM | March 12, 2021, 4:14PM | 24 | 188 | 4 | PP-250 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/22 | Sprint 2 |  | March 9, 2021, 4:58 PM | March 12, 2021, 4:14PM | 24
1.2.3 | implement copy_location_details method |  |  | 8 | 12 | 16 | 16 | Michał | March 15, 2021, 1:07 PM | March 17, 2021, 3:59 PM | 18 | 137 | 6 | PP-251 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/35 | Sprint 2 |  | March 15, 2021, 1:07 PM | March 17, 2021, 3:59 PM | 16
1.2.4 | implement caseLocationDetails endpoint |  | 1.2.1 - 1.2.3 | 4 | 8 | 8 | 8 | Michał | March 17, 2021, 6:32 PM | March 19, 2021, 5:41 PM | 16 | 819 | 373 | PP-252 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/60 | Sprint 3 | postponed from Sprint 2 | March 17, 2021, 6:32 PM | March 19, 2021, 5:41 PM | 8
1.3 | caseLobCounts endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-253 | [5 empty] | 0
1.3.1 | implement get_lob_statistics in PandasAnalyticalService |  | 1.1.8 | 4 | 4 | 4 | 4 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-254 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 4
1.3.2 | implement copy_lob_statistics method |  |  | 3.5 | 4 | 2 | 2 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-255 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 2
1.3.3 | Implement caseLobCounts endpoint | see design | 1.3.1, 1.3.2 | 1 | 2 | 4 | 4 | Aleksandra | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 1 | 60 | 4 | PP-256 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/21 | Sprint 2 |  | March 11, 2021, 5:22 PM | March 11, 2021, 7:48 PM | 4
1.4 | getAvailableYears endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-257 | [5 empty] | 0
1.4.1 | Implement get_all_years method in PandasAnalitycalService |  | 1.1.8 | 2 | 2 | 2 | 2 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:25 AM | 2 | 50 | 13 | PP-258 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/25 | Sprint 2 |  | March 12, 2021, 1:52 PM | March 15, 2021, 11:25 AM | 2
1.4.2 | Implement get_row_range helper method for pandas DF |  |  | 1 | 2 | 4 | 4 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:28 AM | 2 | 30 | 1 | PP-259 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/26 | Sprint 2 |  | March 12, 2021, 1:52 PM | March 15, 2021, 11:28 AM | 4
1.4.3 | Implement getAvailableYears endpoint | see design | 1.4.1, 1.4.2 | 1 | 2 | 4 | 4 | Aleksandra | March 12, 2021, 1:52 PM | March 15, 2021, 11:29 AM | 2 | 47 | 0 | PP-260 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/27 | Sprint 2 |  | March 12, 2021, 1:52 PM | March 15, 2021, 11:29 AM | 4
1.5 | getDateTimeStatsForListOfYears endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-261 | [5 empty] | 0
1.5.1 | implement get_quarterly_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | 4 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-262 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 4
1.5.2 | implement copy_quarterly_statistics method |  |  | 2 | 2 | 2 | 2 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-263 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 2
1.5.3 | implement getDateTimeStatsForListOfYears endpoint | see design | 1.5.1, 1.5.2 | 2 | 2 | 4 | 4 | Tomek We | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 5 | 67 | 7 | PP-264 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/23 | Sprint 2 |  | March 11, 2021, 11:55 AM | March 12, 2021, 6:17 PM | 4
1.6 | implement filteredCareUnitTypes endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-265 | [5 empty] | 0
1.6.1 | Implement get_careunit_statistics method in PandasAnalyticalService |  | 1.1.8 | 3 | 4 | 4 | 4 | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 | PP-285 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 4
1.6.2 | Implement extract_careunit_statistics method |  |  | 2 | 2 | 4 | 4 | Tomek We | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 9 | 72 | 3 | PP-286 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | March 5, 2021, 3:33 PM | March 10, 2021, 6:12 PM | 4
1.6.3 | Implement filteredCareUnitTypes endpoint | see design | 1.6.1, 1.6.2 | 1 | 2 | 4 | 4 | Tomek We | March 9, 2021, 11:43 AM | March 10, 2021, 6:12 PM | 9 | 74 | 4 | PP-265 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/18 | Sprint 2 |  | March 9, 2021, 11:43 AM | March 10, 2021, 6:12 PM | 4
1.7 | implement getDatasetsInitialFilters | see design |  |  |  |  | 0 | [6 empty] | PP-288 | [5 empty] | 0
1.7.1 | Implement get_diagnose_statistics method in PandasAnalyticalService |  | 1.1.8 | 3.5 | 4 | 4 | 4 | Aleksandra | February 25, 2021, 2:55 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-289 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. | February 25, 2021, 2:55 PM | March 4, 2021, 01:19 AM | 4
1.7.2 | implement copy_diagnose_statistics method |  |  | 2 | 2 | 2 | 2 | Aleksandra | March 1, 2021, 5:02 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-290 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. | March 1, 2021, 5:02 PM | March 4, 2021, 01:19 AM | 2
1.7.3 | implement getDatasetsInitialFilters endpoint | use existing queries / methods to populate data in the requested fields | 1.3, 1.4, 1.5, 1.6 | 6 | 6 | 4 | 4 | Aleksandra | March 1, 2021, 5:03 PM | March 4, 2021, 01:19 AM | 16 | 247 | 4 | PP-291 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/12 | Sprint 1 | Added during sprint, due to earlier finish of research tasks. Task to be finished - dependencies have to be implemented later. | March 1, 2021, 5:03 PM | March 4, 2021, 01:19 AM | 4
1.8 | filteredCareUnits endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-371 | [5 empty] | 0
1.8.3 | Implement format_careunits method |  |  | 3.5 | 4 | 4 | 4 | Manoj | April 8, 2021, 5:11 PM | April 8, 2021, 5:11 PM | 5 | 40 | 3 | PP-375 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/115 | Sprint 4 |  | April 8, 2021, 5:11 PM | April 8, 2021, 5:11 PM | 4
1.8.4 | Implement filteredCareUnits endpoint |  | 1.6, 1.8.3, 1.13 | 8 | 4 | 10 | 10 | Manoj | April 8, 2021, 6:52 PM | April 9, 2021, 3:44 PM | 9 | 122 | 2 | PP-376 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/119 | Sprint 4 |  | April 8, 2021, 6:52 PM | April 9, 2021, 3:44 PM | 10
1.9 | searchCareUnitAndDetail endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-377 | [5 empty] | 0
1.9.1 | Implement make_hospital_node |  |  | 1 | 1 | 2 | 2 | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 | PP-378 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2 | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 2
1.9.2 | Implement make_entity_node |  |  | 2.5 | 2 | 2 | 2 | Aleksandra | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 3 | 21 | 0 | PP-379 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/44 | Sprint 2 | Added to sprint in Sprint 2 | March 16, 2021, 5:07 PM | March 17, 2021, 2:11 PM | 2
1.9.3 | Handle result_set argument in the group_nodes method (inside PandasAnalyticalService) | handle only SHORT and FULL GroupNodesResultSet values | 1.1.12 | 5 | 12 | 16 | 16 | Aleksandra | March 17, 2021, 5:44 PM | March 17, 2021, 8:03 PM | 2.5 | 107 | 26 | PP-380 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/47 | Sprint 2 | Added to sprint in Sprint 2 | March 17, 2021, 5:44 PM | March 17, 2021, 8:03 PM | 16
1.9.4 | Modify extract_node_statistics to extract full result | extract 60-day readmission statistics when available | 1.1.13 | 2.5 | 4 | 4 | 4 | Manoj | March 22, 2021, 5:34 PM | March 22, 2021, 4:16 PM | 4 | 65 | 6 | PP-381 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/61 | Sprint 3 | Problem with actual time estimation, because of not updated jira | March 22, 2021, 5:34 PM | March 22, 2021, 4:16 PM | 4
1.9.5 | Implement get_careunit_details method |  | 1.1.15, 1.9.4 | 4 | 4 | 6 | 6 | Manoj | March 22, 2021, 5:35 PM | March 22, 2021, 7:43 AM | 6 | 133 | 8 | PP-382 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/62 | Sprint 3 |  | March 22, 2021, 5:35 PM | March 22, 2021, 7:43 AM | 6
1.9.6 | Implement get_entity_address in PandasAnalyticalService | provide required datasets | 1.1.9 | 8 | 6 | 8 | 8 | Manoj | March 18, 2021, 8:14 AM | March 19, 2021, 4:28 PM | 16 | 41 | 1 | PP-383 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/58 | Sprint 3 | Problem with actual time estimation, because of not updated jira | March 18, 2021, 8:14 AM | March 19, 2021, 4:28 PM | 8
1.9.7 | Implement make_address method |  |  | 1 | 1 | 2 | 2 | Manoj | March 19, 2021, 4:55 PM | March 19, 2021, 4:43PM | 2 | 24 | 1 | PP-384 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/59 | Sprint 3 | Problem with actual time estimation, because of not updated jira | March 19, 2021, 4:55 PM | March 19, 2021, 4:43PM | 2
1.9.8 | Implement get_entity_quality in PandasAnalyticalService |  | 1.9.6 | 26 | 32 | 36 | 36 | Bartek | March 31, 2021, 3:15 PM | April 6, 2021, 8:52 AM | 16.5 | 403 | 6 | PP-385 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/106 | Sprint 4 | Sprint 3, sprint 4 | March 31, 2021, 3:15 PM | April 6, 2021, 8:52 AM | 36
1.9.9 | Implement make_quality method |  |  | 1 | 1 | 1 | 1 | Manoj | March 24, 2021, 2:00 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-386 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira | March 24, 2021, 2:00 PM | March 24, 2021, 10:24 AM | 1
1.9.10 | Implement get_facility_details in PandasAnalyticalService |  | 1.9.6 | 18 | 16 | 24 | 24 | Bartek | April 6, 2021, 9:38 AM | April 6, 2021, 2:29 PM | 5 | 116 | 9 | PP-387 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/109 | Sprint 4 | Postponed from sprint 3 (lower priority) | April 6, 2021, 9:38 AM | April 6, 2021, 2:29 PM | 24
1.9.11 | Implement make_facility method |  |  | 1 | 1 | 2 | 2 | Manoj | March 24, 2021, 2:02 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-388 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 | Problem with actual time estimation, because of not updated jira | March 24, 2021, 2:02 PM | March 24, 2021, 10:24 AM | 2
1.9.12 | Implement get_entity_staffing in PandasAnalyticalService |  | 1.9.6 | 4 | 4 | 4 | 4 | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:31 AM | 4 | 33 | 0 | PP-389 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/71 | Sprint 3 |  | March 23, 2021, 5:03 PM | March 24, 2021, 10:31 AM | 4
1.9.13 | Implement make_staffing method |  |  | 1 | 1 | 2 | 2 | Manoj | March 23, 2021, 5:03 PM | March 24, 2021, 10:24 AM | 1.66 | 11 | 1 | PP-390 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/70 | Sprint 3 |  | March 23, 2021, 5:03 PM | March 24, 2021, 10:24 AM | 2
1.9.14 | Implement searchCareUnitAndDetail endpoint |  | 1.9.1 - 1.9.13 | 8 | 8 | 10 | 10 | Bartek | April 6, 2021, 3:10 PM |  |  |  |  | PP-391 |  | Sprint 4 | Postponed from sprint 3 (lower priority) | April 6, 2021, 3:10 PM | 2021-04-16 | 0
1.10 | getDateTimesForYear endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-392 | [5 empty] | 0
1.10.1 | Implement find_fiscal_quarters method in PandasAnalyticalService |  | 1.1.9 | 3 | 2 | 8 | 8 | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 | PP-393 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2 | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 8
1.10.2 | Implement getDateTimesForYear endpoint |  | 1.10.1 | 3 | 2 | 4 | 4 | Bartek | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 5 | 59 | 6 | PP-394 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/33 | Sprint 2 | Added to sprint in Sprint 2 | March 16, 2021, 11:54 AM | March 17, 2021, 1:29 PM | 4
1.11 | Benchmark Calculation | see design |  |  |  |  | 0 | [6 empty] | PP-395 | [5 empty] | 0
1.11.1 | Implement get_dataset_properties in the DatasetService | see DatasetService design | DM | 4 | 3 | 8 | 8 | [6 empty] | PP-396 | [5 empty] | 0
1.11.2 | Implement set_dataset_properties in DatasetService |  | DM | 6 | 3 | 8 | 8 | [6 empty] | PP-397 | [5 empty] | 0
1.11.3 | Implement find_datasets in DatasetService |  | DM | 4 | 4 | 4 | 4 | [6 empty] | PP-398 | [5 empty] | 0
1.11.4 | Implement get_time_range in PandasAnalyticalService |  | 1.1.8 | 3 | 2 | 4 | 4 | Bartek | March 18, 2021, 12:36 PM | March 19, 2021, 12:25 PM | 8 | 33 | 3 | PP-399 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/50 | Sprint 2 | Added to sprint in Sprint 2 | March 18, 2021, 12:36 PM | March 19, 2021, 12:25 PM | 4
1.11.5 | Implement find_dataset_time_range | use mock DatasetService for tests |  | 4 | 3 | 4 | 4 | Bartek | March 19, 2021, 11:36 AM | March 22, 2021, 9:56 AM | 6 | 123 | 12 | PP-400 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/55 | Sprint 3 |  | March 19, 2021, 11:36 AM | March 22, 2021, 9:56 AM | 4
1.11.6 | Implement find_benchmark_datasets method | use mock DatasetService for tests | 1.11.4, 1.11.5 | 6 | 6 | 8 | 8 | Bartek | March 22, 2021, 10:24 AM | March 24, 2021, 4:18 PM | 20 | 153 | 44 | PP-401 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63 | Sprint 3 | Require reimplementation due to misunderstanding of requirements: https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/63 | March 22, 2021, 10:24 AM | March 24, 2021, 4:18 PM | 8
1.11.7 | Implement calculate_benchmark method in PandasAnalyticalService | for now do not implement any special handling of AC_Entity / PAC_Entity nodes, do not handle packed nodes | 1.1.8 | 40 | 40 | 48 | 48 | Michał | March 19, 2021, 6:26 PM | April 9, 2021, 3:54 PM | 38.5 | 396 | 2 | PP-402 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/120 | Sprint 4 | Delayed significantly due to COVID | March 19, 2021, 6:26 PM | April 9, 2021, 3:54 PM | 48
1.11.8 | Implement get_service_line in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 | 4 | Bartek | March 23, 2021, 9:49 AM | March 24, 2021, 4:39 PM | 6 | 31 | 1 | PP-403 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/67 | Sprint 3 |  | March 23, 2021, 9:49 AM | March 24, 2021, 4:39 PM | 4
1.11.9 | Implement get_clinical_episode in PandasAnalyticalService |  | 1.1.8 | 3 | 3 | 4 | 4 | Bartek | March 23, 2021, 3:19 PM | March 24, 2021, 4:23PM | 4 | 25 | 2 | PP-404 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/68 | Sprint 3 |  | March 23, 2021, 3:19 PM | March 24, 2021, 4:23PM | 4
1.11.10 | Implement get_parent_node method |  | 1.11.8, 1.11.9 | 3 | 2 | 4 | 4 | Bartek | March 24, 2021, 2:54 PM | March 25, 2021, 11:27 PM | 4 | 95 | 9 | PP-405 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/74 | Sprint 3 |  | March 24, 2021, 2:54 PM | March 25, 2021, 11:27 PM | 4
1.11.11 | Handle parent nodes in calculate_benchmark method | see design | 1.11.7 | 12 | 8 | 16 | 16 | Michał | April 9, 2021, 5:17 PM | April 13, 2021, 8:10 PM | 20.5 | 235 | 95 | PP-406 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/129 | Sprint 4 | Postponed from sprint 3 (lower priority) | April 9, 2021, 5:17 PM | 2021-04-13 | 16
1.11.12 | Implement extract_time_range method | see design |  | 3.5 | 3 | 4 | 4 | Michał | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 2 | 20 | 1 | PP-407 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/72 | Sprint 3 |  | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 4
1.11.13 | Implement make_filter (from time range) method | see design | 1.11.12 | 1.5 | 3 | 4 | 4 | Michał | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 2 | 20 | 1 | PP-408 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/72 | Sprint 4 | Postponed from sprint 3 (lower priority) | March 24, 2021, 10:47 AM | March 24, 2021, 4:00 PM | 4
1.11.14 | Extract benchmark_value in extract_relation_statistics method | see design | 1.1.14 | 6 | 8 | 16 | 16 | Michał | March 25, 2021, 9:55 AM | March 25, 2021, 3:55 PM | 6 | 40 | 0 | PP-409 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/78 | Sprint 3 |  | March 25, 2021, 9:55 AM | March 25, 2021, 3:55 PM | 16
1.11.15 | Handle benchmark future argument in CaseSummaryQueryRunner |  | 1.1.17 | 16 | 16 | 16 | 16 | Tomek We | April 8, 2021, 11:26 AM | April 9, 2021, 5:47 PM | 14 | 117 | 25 | PP-410 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/122 | Sprint 4 |  | April 8, 2021, 11:26 AM | April 9, 2021, 5:47 PM | 16
1.11.16 | Integrate benchmark calculations with the caseSummaryCollection query | see design | 1.11.4 - 1.11.15 | 24 | 24 | 32 | 32 | Aleksandra | [5 empty] | PP-411 |  | Sprint 5 | Will be done in sprint 4 and sprint 5 |  |  | 0
1.11.17 | Implement handling of packed nodes in calculate_benchmark (use decompose_packed_nodes decorator) | see design, implement a unit test for this use case | 1.14.7, 1.14.11 | 6 |  | 8 | 8 | [6 empty] | PP-503 |  | Sprint 5 |  |  |  | 0
1.11.18 | Add source / destination to CaseSummaryType in format_relation_statistics | fix extract_relation_statistics to populate lhs_node and rhs_node in RelationStatistics, then use those members to populate CaseSummaryType in format_relation_statistics |  | 1.5 |  |  | 1.5 | Michał | April 14, 2021, 5:20 PM | April 14, 2021, 5:56 PM |  |  |  | PP-704 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/134 | Sprint 4 | Added to sprint in Sprint 4 |  |  | 0
1.12 | Node Expand and Collapse | see design |  |  |  |  | 0 | [6 empty] | PP-460 | [5 empty] | 0
1.12.1 | Implement extract_action method | see design |  | 4 | 4 | 8 | 8 | Aleksandra | April 6, 2021, 3:21 PM | April 6, 2021, 3:21 PM | 6 | 158 | 3 | PP-461 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/110 | Sprint 5 |  | April 6, 2021, 3:21 PM | April 6, 2021, 3:21 PM | 8
1.12.2 | Implement make_filter_from_node method | see design | 1.1.7, 1.1.21 - 1.1.23 | 4 | 4 | 8 | [7 empty] | PP-462 |  | Sprint 5 | Abandoned - method already exists. |  |  | 0
1.12.3 | Implement extract_filters method | extracting filters from list of actions | 1.12.1, 1.12.2 | 2 | 2 | 4 | 4 | Aleksandra | April 6, 2021, 3:45 PM |  |  |  |  | PP-463 |  | Sprint 5 |  | April 6, 2021, 3:45 PM | 2021-12-04 | 0
1.12.4 | Integrate expand / collapse functionality with the caseSummaryCollection query | see design | 1.1, 1.12.1 - 1.12.3 | 22 | 24 | 32 | 32 | Aleksandra | [5 empty] | PP-464 |  | Sprint 5 |  |  |  | 0
1.13 | find_child_nodes | see design |  |  |  |  | 0 | [6 empty] | PP-465 | [5 empty] | 0
1.13.1 | Implement get_child_node_columns method |  |  | 3.5 | 4 | 4 | 4 | Tomek We | March 17, 2021, 6:53 PM | March 18, 2021, 12:32 PM | 4 | 128 | 28 | PP-454 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/48 | Sprint 2 | Added to sprint in Sprint 2 | March 17, 2021, 6:53 PM | March 18, 2021, 12:32 PM | 4
1.13.2 | Implement find_child_nodes method in PandasAnalyticalService, for now without sorting | implement first version without sorting or handing other options (dry_run, pagination, match_prefix) | 1.13.1, 1.9.1 | 32 | 24 | 32 | 32 | Tomek We | March 18, 2021, 1:52 PM | March 18, 2021, 8:25 PM | 6.5 | 151 | 5 | PP-455 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/52 | Sprint 2 | Added to sprint in Sprint 2 | March 18, 2021, 1:52 PM | March 18, 2021, 8:25 PM | 32
1.13.3 | Handle sorting by case_count in find_child_nodes, add case_count property in Node class | see design, also set case_count property in returned nodes, for now we can allow only sorting by 1 sort criteria | 1.13.2 | 8 | 4 | 12 | 12 | Tomek We | March 18, 2021, 7:36 PM | March 19, 2021, 12:10 PM | 5 | 95 | 3 | PP-456 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/53 | Sprint 2 | Added to sprint in Sprint 2 | March 18, 2021, 7:36 PM | March 19, 2021, 12:10 PM | 12
1.13.4 | Handle sorting by options 2 - 7 in find_child_nodes | also handle sorting by multiple columns | 1.13.3 | 32 | 20 | 32 | 32 | Tomek We | March 22, 2021, 10:20 AM | March 23, 2021, 11:17 AM | 8 | 191 | 21 | PP-466 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/64 | Sprint 3 |  | March 22, 2021, 10:20 AM | March 23, 2021, 11:17 AM | 32
1.13.5 | Handle sorting by rating in find_child_nodes |  | 1.13.4 | 6 | 8 | 10 | 10 | Tomek We | March 31, 2021, 5:17 PM | March 31, 2021, 6:40 PM | 1 | 34 | 1 | PP-467 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/98 | Sprint 3 |  | March 31, 2021, 5:17 PM | March 31, 2021, 6:40 PM | 10
1.13.6 | Handle sorting by name in find_child_nodes |  | 1.13.4 | 24 | 24 | 32 | 32 | Tomek We | March 23, 2021, 11:20 AM | March 23, 2021, 12:22AM | 7 | 74 | 27 | PP-468 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/65, https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/69 | Sprint 3 | Planned in Sprint 4 | March 23, 2021, 11:20 AM | March 23, 2021, 12:22AM | 32
1.13.7 | Handle pagination argument | Limit results to a specific page only | 1.13.2 | 3.5 | 4 | 4 | 4 | Tomek We | March 29, 2021, 3:28 PM | March 29, 2021, 4:20 PM | 1 | 39 | 1 | PP-469 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/90 | Sprint 3 |  | March 29, 2021, 3:28 PM | March 29, 2021, 4:20 PM | 4
1.13.8 | Handle match_prefix argument |  | 1.13.6 | 8 | 4 | 8 | 8 | Tomek We | March 29, 2021, 12:34 PM | March 29, 2021, 1:22 PM | 1 | 31 | 0 | PP-470 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/88 | Sprint 3 | Planned in Sprint 4 | March 29, 2021, 12:34 PM | March 29, 2021, 1:22 PM | 8
1.13.9 | Handle dry_run option | return int when dry_run = True | 1.13.2 | 8 | 4 | 8 | 8 | Michał | April 1, 2021, 12:31 PM | April 1, 2021, 2:07 PM | 2 |  |  | PP-471 |  | Sprint 3 |  | April 1, 2021, 12:31 PM | April 1, 2021, 2:07 PM | 8
1.14 | Sorting and Pagination of Nodes | see design |  |  |  |  | 0 | [6 empty] | PP-472 | [5 empty] | 0
1.14.1 | Implement extract_sort_criteria method |  | 1.13.2 | 3 | 4 | 4 | 4 | Michał | March 25, 2021, 4:42 PM | March 26, 2021, 1:00 PM | 5 | 67 | 2 | PP-473 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/82 | Sprint 3 | Added to sprint in Sprint 3 | March 25, 2021, 4:42 PM | March 26, 2021, 1:00 PM | 4
1.14.2 | Implement pack_nodes method, add is_packed() and unpack() methods to Node class | see design, make sure to check performance for ~40k nodes | 1.1.7 | 20 | 24 | 24 | 24 | Bartek | March 25, 2021, 12:45 PM | March 26, 2021, 9:20 AM | 8 | 90 | 12 | PP-474 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/79 | Sprint 3 | Added to sprint in Sprint 3 | March 25, 2021, 12:45 PM | March 26, 2021, 9:20 AM | 24
1.14.3 | Implement extract_pagination method |  |  | 2 | 4 | 4 | 4 | Michał | March 26, 2021, 1:07 PM | March 26, 2021, 3:16 PM | 2 | 29 | 3 | PP-475 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/83 | Sprint 3 | Added to sprint in Sprint 3 | March 26, 2021, 1:07 PM | March 26, 2021, 3:16 PM | 4
1.14.4 | Implement get_graph_orientation method |  |  | 3.5 | 4 | 4 | 4 | Michał | March 26, 2021, 5:53 PM | March 29, 2021, 9:17 AM | 4 | 245 | 6 | PP-476 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/86 | Sprint 3 | Added to sprint in Sprint 3 | March 26, 2021, 5:53 PM | March 29, 2021, 9:17 AM | 4
1.14.5 | Implement extract_graph_pagination method |  | 1.14.3, 1.14.4 | 2 | 4 | 4 | 4 | Michał | March 29, 2021, 10:14 AM | March 29, 2021, 1:29 PM | 2.5 | 34 | 3 | PP-477 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/89 | Sprint 3 | Added to sprint in Sprint 3 | March 29, 2021, 10:14 AM | March 29, 2021, 1:29 PM | 4
1.14.6 | Update group_nodes method in PandasAnalyticalService to allow a single packed node on either side (and up to 2 pack nodes in total) | see design | 1.14.2 | 24 | 32 | 32 | 32 | Maciej | March 26, 2021, 9:22 AM | April 2, 2021, 5:27 PM | 20.83 | 164 | 10 | PP-478 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/105 | Sprint 4 |  | March 26, 2021, 9:22 AM | April 2, 2021, 5:27 PM | 32
1.14.11 | Handle single packed node on each side in calculate_benchmark method | see also 1.14.6 | 1.11.7, 1.14.6 | 12 | 20 | 26 | 12 | Tomek We | [5 empty] | PP-504 |  | Sprint 4 | Postponed, due to bug fixing: PP-1003 | 2021-04-14 | 2021-04-16 | 0
1.14.7 | Implement decompose_packed_nodes decorator | Apply decorator to all group_nodes implementations (see design), make sure to run queries in parallel |  | 8 | 8 | 8 | 8 | Bartek | March 29, 2021, 3:01 PM | April 6, 2021, 1:01 PM | 7 | 134 | 8 | PP-479 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/92 | Sprint 4 |  | March 29, 2021, 3:01 PM | April 6, 2021, 1:01 PM | 8
1.14.8 | Refactor make_abstract_graph_query to use find_child_nodes method | pass sorting criteria, see updated design, make sure to run lhs/rhs queries in parallel | 1.1.10, 1.13.3, 1.14.1 | 20 | 24 | 24 | 24 | Maciej | April 7, 2021, 3:41 PM | April 9, 2021, 1:28 PM | 22.58 | 176 | 65 | PP-480 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/118 | Sprint 4 |  | April 7, 2021, 3:41 PM | April 9, 2021, 1:28 PM | 24
1.14.9 | Refactor AbstractGraphModel class and make_abstract_graph_model method to reflect design | make sure to pack nodes according to rules, see design | 1.14.1 - 1.14.5 | 12 | 16 | 16 | 16 | Michał | March 29, 2021, 2:21 PM | March 31, 2021, 6:16 PM | 16.5 | 235 | 66 | PP-481 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/97 | Sprint 3 | Added to sprint in Sprint 3 | March 29, 2021, 2:21 PM | March 31, 2021, 6:16 PM | 16
1.14.12 | Implement make_abstract_graph_model special case to handle pagination (0,0) | see design | 1.14.9 | 1 |  |  | 1 | Maciej | April 6, 2021, 10:02 AM | April 6, 2021, 11:58 AM | 3.5 | 27 | 3 | PP-623 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/108 | Sprint 4 |  | April 6, 2021, 10:02 AM | April 6, 2021, 11:58 AM | 1
1.14.10 | Update caseSummaryCollection endpoint to handle sorting and pagination | make sure sorting and pagination rules are processed, add unit tests for this functionality | 1.14.1 - 1.14.9 | 8 | 8 | 8 | 8 | Tomek We | [5 empty] | PP-482 |  | Sprint 4 |  | 2021-04-16 | 2021-04-19 | 0
1.15 | allDatasets endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-483 | [5 empty] | 0
1.15.1 | define the DatasetDetails class |  |  | 2 | 1 | 4 | 4 | Tomek We | March 24, 2021, 5:51 PM | March 24, 2021, 6:08 PM | 1 | 15 | 0 | PP-505 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/73 | Sprint 3 | Added to sprint in Sprint 3 | March 24, 2021, 5:51 PM | March 24, 2021, 6:08 PM | 4
1.15.2 | Implement get_all_datasets method in the DatasetService class | order by upload_time descending | DM | 12 | 12 | 16 | 16 | Kamil C | April 14, 2021, 12:02 PM |  |  |  |  | PP-484 |  | Sprint 5 |  |  |  | 0
1.15.3 | Implement format_all_datasets_response method |  | 1.15.1 | 1.5 | 1 | 1 | 1 | Tomek We | March 25, 2021, 5:16 PM | March 25, 2021, 7:42 PM | 2.5 | 1024 | 871 | PP-506 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/80 | Sprint 3 | Added to sprint in Sprint 3 | March 25, 2021, 5:16 PM | March 25, 2021, 7:42 PM | 1
1.15.4 | Implement DummyDatasetService | This is to run P2 application without the actual DM implementation yet, do not implement any unit tests for this class |  | 3.5 | 8 | 8 | 8 | Tomek We | March 25, 2021, 11:22 AM | March 25, 2021, 3:22 PM | 4 | 141 | 5 | PP-518 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/76 | Sprint 3 | Added to sprint in Sprint 3 | March 25, 2021, 11:22 AM | March 25, 2021, 3:22 PM | 8
1.15.5 | Implement allDatasets endpoint | use DummyDatasetService for now | 1.15.3, 1.15.4 | 3 | 4 | 4 | 4 | Tomek We | March 26, 2021, 11:43 AM | March 26, 2021, 4:41 PM | 4 | 131 | 9 | PP-507 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/85 | Sprint 3 | Added to sprint in Sprint 3 | March 26, 2021, 11:43 AM | March 26, 2021, 4:41 PM | 4
1.16 | getLdsDatasetsIds endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-508 | [5 empty] | 0
1.16.1 | Implement getLDSDatasetsIDs endpoint | use mock DatasetService for now |  | 3 | 4 | 4 | 4 | Tomek We | March 29, 2021, 10:23 AM | March 29, 2021, 11:14 AM | 1 | 37 | 3 | PP-509 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/87 | Sprint 3 | Added to sprint in Sprint 3 | March 29, 2021, 10:23 AM | March 29, 2021, 11:14 AM | 4
1.17 | dataset endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-510 | [5 empty] | 0
1.17.1 | Implement get_datasets method in DatasetService | 1.15.2 | DM | 3.5 | 4 | 4 | 4 | Kamil C | [5 empty] | PP-511 |  | Sprint 5 |  |  |  | 0
1.17.2 | Implement get_pipeline_statistics method in DatasetService | connect to the Pipeline Server | O2Grouper | 24 | 24 | 24 | 24 | [6 empty] | PP-512 | [5 empty] | 0
1.17.3 | Implement dataset endpoint |  | 1.17.1, 1.17.2 | 4 | 8 | 8 | 8 | [6 empty] | PP-513 | [5 empty] | 0
1.18 | caseStatistics endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-514 | [5 empty] | 0
1.18.1 | Implement get_case_statistics in PandasAnalyticalService | Handle sorting and limitation of results | 1.1.8 | 24 | 24 | 32 | 32 | Maciej | April 9, 2021, 4:01 PM |  |  |  |  | PP-519 |  | Sprint 4 |  | April 9, 2021, 4:01 PM | 2021-04-15 | 0
1.18.2 | Implement get_serviceline_benchmarks in PandasAnalyticalService | similar to 1.19.2 | 1.1.8 | 12 | 8 | 16 | 16 | Manoj | April 13, 2021, 11:16 AM |  |  |  |  | PP-520 |  | Sprint 4 |  | 2021-04-13 | 2021-04-15 | 0
1.18.3 | Implement join_serviceline_benchmarks | similar to 1.19.3 |  | 3 | 3 | 4 | 4 | Manoj | April 12, 2021, 1:20 PM | April 12, 2021, 1:21 PM | 5 | 76 | 1 | PP-521 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/126 | Sprint 4 |  | April 12, 2021, 1:20 PM | 2021-04-12 | 4
1.18.4 | Implement format_case_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 5 | 3 | 8 | 8 | Manoj | April 12, 2021, 4:55 PM | April 12, 2021, 4:55 PM | 5 | 147 | 4 | PP-522 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/127 | Sprint 4 |  | 2021-04-12 | 2021-04-13 | 8
1.18.5 | Implement caseStatistics endpoint | see design, make sure to run queries in parallel | 1.18.1 - 1.18.4, 1.21 | 17 | 12 | 20 | 20 | [6 empty] | PP-523 |  | Sprint 4 |  |  |  | 0
1.19 | caseSummaryCollectionMapView endpoint | see design |  |  |  |  | 0 | [6 empty] | PP-515 | [5 empty] | 0
1.19.1 | Implement get_map_view_entity_statistics in PandasAnalyticalService |  | 1.1.8 | 16 | 16 | 20 | 20 | Michał | [5 empty] | PP-524 |  | Sprint 4 | Started in Sprint 4, will be finished in Sprint 5 |  |  | 0
1.19.2 | Implement get_careunit_benchmarks in PandasAnalyticalService |  | 1.1.8 | 14 | 12 | 20 | 20 | [6 empty] | PP-525 | [5 empty] | 0
1.19.3 | Implement join_careunit_benchmarks | Prepare sythetic data frames for the unit test |  | 3 | 3 | 4 | 4 | [6 empty] | PP-526 | [5 empty] | 0
1.19.4 | Implement format_entity_statistics | Prepare synthetic data frames for unit tests (without and with benchmark values) |  | 4 | 3 | 4 | 4 | [6 empty] | PP-527 | [5 empty] | 0
1.19.5 | Implement caseSummaryCollectionMapView endpoint | see design, make sure to run queries in parallel | 1.19.1 - 1.19.4 | 16 | 12 | 12 | 12 | [6 empty] | PP-528 | [5 empty] | 0
1.20 | Error Handling | see design (to be modified) |  |  |  |  | 0 | [6 empty] | PP-529 | [5 empty] | 0
1.20.1 | Define ApplicationError base class and app_error_class decorator | just copy from the design and add unit tests |  | 3 |  | 2 | 2 | [6 empty] | PP-530 |  | Sprint 5 |  |  |  | 0
1.20.2 | Review application's code, find all raise statements and throw proper errors | Declare proper exception classes, define error variables, use DatasetNotFound as a model example, place all errors in the errors.py module | 1.1 - 1.19 | 28 |  | 36 | 36 | [6 empty] | PP-531 |  | Sprint 5 |  |  |  | 0
1.20.3 | Add list of error codes and descriptions to technical design | This task is development driven |  | 6 |  | 4 | 4 | Wojtek | [5 empty] | PP-532 |  | Sprint 5 |  |  |  | 0
1.21 | Backend Configuration | see design |  |  |  |  | 0 | [6 empty] | PP-533 | [5 empty] | 0
1.21.1 | Implement AppConfig singleton | Define ConfigVariables and defaults, validate configuration on first access to AppConfig |  | 12.5 |  | 16 | 12.5 | Tomek We | April 12, 2021, 12:16 PM | April 12, 2021, 5:40 PM | 7 | 233 | 22 | PP-534 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/128 | Sprint 4 | Added to sprint in Sprint 4 | April 12, 2021, 12:16 PM | 14/04/2021 | 12.5
1.22 | Data Suppression (LDS-11 rule) | see design |  |  |  |  | 0 | [6 empty] | PP-537 | [5 empty] | 0
1.22.1 | Implement get_aggregation_level method | see design |  | 3 |  |  | 3 | [6 empty] | PP-1016 | [5 empty] | 0
1.22.2 | Add LDS_SUPPRESSION_ENABLED flag to AppConfig | allow False only in DEBUG deployment mode |  | 2 |  |  | 2 | [6 empty] | PP-1017
1.22.3 | Handle __lds_suppress_aggregation_level member in select_from_relations method from SQLAnalyticalService | implement suppression logic, read tutorial | 1.22.2, 1.24.6 | 28 |  |  | 28 | [6 empty] | PP-1018
1.22.4 | Modify open method in SQLAnalyticsProvider | pass lds_tables argument to SQLAnalyticalService and forward lds_suppress_aggregation_level, see design | 1.24.9 | 3 |  |  | 3 | [6 empty] | PP-1019
1.22.5 | Integrate LDS suppression rules with the caseSummaryCollection endpoint | use get_aggregation_level method and pass its result to open in the AnalyticsProvider, implement unit tests to check if proper aggregation level is passed for various queries, check LDS_SUPPRESSION_ENABLED flag |  | 6 |  |  | 6 | [6 empty] | PP-1020
1.22.6 | Integrate with other endpoints | Review all places where the method "open" from AnalyticsProvider is being called, pass lds_suppress_aggregation_level argument where it makes sense |  | 12 |  |  | 12 | [6 empty] | PP-1021
1.22.7 | Implement is_suppressed method in SQLAnalyticalService | define new method in AnalyticalService base class, always return False from the PandasAnalyticalService |  | 1.5 |  |  | 1.5 | [6 empty] | PP-1022
1.22.8 | Return isSuppressed flag in caseSummaryCollection result | see design |  | 3 |  |  | 3 | [6 empty] | PP-1023
1.23 | User Dataset Upload | see design | [11 empty] | PP-538 | [5 empty] | 0
1.23.16 | Add PIPELINE_SERVER_URL variable to AppConfig | only required in RELEASE deployments | 1.21 | 1 |  |  | 1 | [6 empty] | PP-1024
1.23.1 | Implement add_uploaded_file in Repository class | see design, define repository data model (use Django), add Repository instance to context (available to endpoint resolvers) | 1.23.16 | 10 |  |  | 10 | [6 empty] | PP-942 | [5 empty] | 0
1.23.2 | Implement set_error method in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | [6 empty] | PP-943 | [5 empty] | 0
1.23.3 | Implement set_s3_url method in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | [6 empty] | PP-944 | [5 empty] | 0
1.23.4 | Implement set_pipeline_id in Repository class |  | 1.23.1 | 1.5 |  |  | 1.5 | [6 empty] | PP-945 | [5 empty] | 0
1.23.5 | Implement AppProcessPool class | just copy code from the design |  | 1 |  |  | 1 | [6 empty] | PP-1025 | [5 empty] | 0
1.23.6 | Implement start_o2_grouper method | see design | 1.21 | 3 |  |  | 3 | [6 empty] | PP-1026 | [5 empty] | 0
1.23.7 | Implement upload_to_s3_and_start_o2_grouper method | see design | 1.23.1 - 1.23.6 | [10 empty] | PP-1027 | [5 empty] | 0
1.23.8 | Implement sendfile/upload_file endpoint | copy from P2 v2 backend, run upload_to_s3_and_start_o2_grouper form in a separate process task and return immediately | 1.23.7 | 10 |  |  | 10 | [6 empty] | PP-1028 | [5 empty] | 0
1.23.9 | Implement has_s3_put_object_permission method | see design | 1.21 | 3 |  |  | 3 | [6 empty] | PP-1029 | [5 empty] | 0
1.23.10 | Validate s3:PutObject permission on start-up (in RELEASE deployment mode only) |  | 1.23.9 | 2.5 |  |  | 2.5 | [6 empty] | PP-1030 | [5 empty] | 0
1.23.11 | Implement get_user_uploaded_files method in Repository class | see design | 1.23.1 | 3 |  |  | 3 | [6 empty] | PP-1031
1.23.12 | Update format_all_datasets_response method to take into account upload_status field in DatasetDetails (Validation, Failed or Finished) |  |  | 3 |  |  | 3 | [6 empty] | PP-1032
1.23.13 | Update allDatasets endpoint to include currently processed and failed processing files | see design | 1.23.11 | 4.5 |  |  | 4.5 | [6 empty] | PP-1033
1.23.14 | Implement get_uploaded_file in Repository | see design | 1.23.1 | 3 |  |  | 3 | [6 empty] | PP-1034
1.23.15 | Update get_datasets method in DatasetService | handle uploaded file ids, see design | 1.23.14 | 6 |  |  | 6 | [6 empty] | PP-1035
1.24 | Snowflake Integration | see design | [11 empty] | PP-539 | [5 empty] | 0
1.24.1 | Implement SQLConnectionFactory and SQLConnection | implement connect and close methods, define and use connection configuration variables | 1.21.1 | 8 | 6 |  | 8 | [6 empty] | PP-946 | [5 empty] | 0
1.24.2 | Implement get_sql_column method | see design |  | 2.5 | 2 |  | 2.5 | [6 empty] | PP-947 | [5 empty] | 0
1.24.3 | Implement make_sql_filter (for ColumnFilter) method | see design | 1.24.2 | 4 | 4 |  | 4 | [6 empty] | PP-948 | [5 empty] | 0
1.24.4 | Implement make_sql_filter (for RangeFilter) method | make sure to handle special "fiscal_date" column name | 1.24.2 | 4 | 4 |  | 4 | [6 empty] | PP-949 | [5 empty] | 0
1.24.5 | Implement make_sql_distance_filter method | or_ combine from AC and PAC entities |  | 4 | 4 |  | 4 | [6 empty] | PP-950 | [5 empty] | 0
1.24.6 | Implement select_from_relations in SQLAnalyticalService | define SQLAnalyticalService class, handle unions, joined tables and additional columns, raise error from unimplemented interface methods, ignore lds_suppress_aggregation_level argument | 1.24.3 - 1.24.5 | 14 | 12 |  | 14 | [6 empty] | PP-951 | [5 empty] | 0
1.24.7 | Implement DataCommons class | see design, implement validation of all datasets | 1.24.1 | 18 | 12 |  | 18 | [6 empty] | PP-952 | [5 empty] | 0
1.24.8 | Implement get_datasets method in DatasetService | see design | DM | 12 |  |  | 12 | [6 empty] | PP-953 | [5 empty] | 0
1.24.9 | Implement SQLAnalyticsProvider | see design, always query DatasetService, make sure to cache Tables, use mocked DatasetService for tests | 1.24.1 |  | 12 | [8 empty] | PP-954 | [5 empty] | 0
1.24.10 | Handle backend type selection from configuration | Check BACKEND_TYPE configuration variable to create either PandasAnalyticsProvider and mocked DatasetService or SQLAnalyticsProvider and real DatasetService | 1.24.1 - 1.24.9 | 10 | 6 |  | 10 | [6 empty] | PP-955 | [5 empty] | 0
1.24.11 | Implement find_child_nodes is SQLAnalyticalService | handle all arguments, use pandas implementation as example | 1.13, 1.24.6 | 24 | 16 |  | 24 | [6 empty] | PP-956 | [5 empty] | 0
1.24.12 | Implement group_nodes in SQLAnalyticalService | see pandas implementation as example | 1.14.6, 1.24.6 | 32 | 32 |  | 32 | [6 empty] | PP-957 | [5 empty] | 0
1.24.13 | Implement get_entity_details in SQLAnalyticalService |  | 1.24.6 | 3 | 3 |  | 3 | [6 empty] | PP-958 | [5 empty] | 0
1.24.14 | Implement get_entity_counts in SQLAnalyticalService |  | 1.24.6 | 12 | 8 |  | 12 | [6 empty] | PP-959 | [5 empty] | 0
1.24.15 | Implement get_lob_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-960 | [5 empty] | 0
1.24.16 | Implement get_quarterly_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-961 | [5 empty] | 0
1.24.17 | Implement get_careunit_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-962 | [5 empty] | 0
1.24.18 | Implement get_diagnose_statistics in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-963 | [5 empty] | 0
1.24.19 | Implement find_fiscal_quarters in SQLAnalyticalService |  | 1.24.6 | 2 | 2 |  | 2 | [6 empty] | PP-964 | [5 empty] | 0
1.24.20 | Implement get_time_range in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-965 | [5 empty] | 0
1.24.21 | Implement calculate_benchmark in SQLAnalyticalService | see pandas implementation as example | 1.11.7, 1.24.6 | 32 | 32 |  | 32 | [6 empty] | PP-966 | [5 empty] | 0
1.24.22 | Implement get_entity_address in SQLAnalyticalService |  | 1.24.6 | 4 | 2 |  | 4 | [6 empty] | PP-967 | [5 empty] | 0
1.24.23 | Implement get_entity_quality in SQLAnalyticalService |  | 1.24.6 | 6 | 8 |  | 6 | [6 empty] | PP-968 | [5 empty] | 0
1.24.24 | Implement get_facility_details in SQLAnalyticalService |  | 1.24.6 | 6 | 8 |  | 6 | [6 empty] | PP-969 | [5 empty] | 0
1.24.25 | Implement get_entity_staffing in SQLAnalyticalService |  | 1.24.6 | 4 | 2 |  | 4 | [6 empty] | PP-970 | [5 empty] | 0
1.24.32 | Impement get_service_unit_ids method in DataCommons | see design, make sure to cache results | 1.24.7 | 4 | 4 |  | 4 | [6 empty] | PP-971 | [5 empty] | 0
1.24.33 | Implement get_service_line in SQLAnalyticalService | use get_service_unit_ids and resolve the ID mapping from its result | 1.24.6 | 1.5 | 1.5 |  | 1.5 | [6 empty] | PP-972 | [5 empty] | 0
1.24.34 | Implement get_clinical_episode in SQLAnalyticalService | use get_service_unit_ids and resolve the ID mapping from its result | 1.24.6 | 1.5 | 1.5 |  | 1.5 | [6 empty] | PP-973 | [5 empty] | 0
1.24.35 | Implement get_map_view_entity_statistics in SQLAnalyticalService | see pandas implementation as example | 1.19.1, 1.24.6 | 10 | 12 |  | 10 | [6 empty] | PP-974 | [5 empty] | 0
1.24.36 | Implement get_case_statistics in SQLAnalyticalService | see pandas implementation as example | 1.18.1, 1.24.6 | 12 | 12 |  | 12 | [6 empty] | PP-975 | [5 empty] | 0
1.24.37 | Implement get_serviceline_benchmarks in SQLAnalyticalService | see pandas implementation as example | 1.18.2, 1.24.6 | 12 | 8 |  | 12 | [6 empty] | PP-976 | [5 empty] | 0
1.24.38 | Implement get_careunit_benchmarks in SQLAnalyticalService | see pandas and 1.24.30 implementation as example | 1.24.30, 1.24.6 | 12 | 8 |  | 12 | [6 empty] | PP-977 | [5 empty] | 0
1.24.39 | Implement get_all_service_line_ids in SQLAnalyticalService | use get_service_unit_ids method result from DataCommons | 1.24.32 | 2.5 | 2 |  | 2.5 | [6 empty] | PP-978 | [5 empty] | 0
1.24.40 | Implement get_unique_drgs in SQLAnalyticalService |  | 1.24.6 | 3 | 2 |  | 3 | [6 empty] | PP-979 | [5 empty] | 0
1.25 | ServiceLine API | see design | [11 empty] | PP-540 | [5 empty] | 0
1.25.1 | Handle parent_node = None for service line nodes in find_child_nodes_method | implement unit test to cover this case | 1.13 | 3 |  |  | 3 | Tomek We | April 13, 2021, 6:09 PM | April 14, 2021, 11:48 AM | 2 | 18 | 2 | PP-980 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/131 | Sprint 4 | Added to sprint in Sprint 4 |  |  | 3
1.25.2 | Implement filteredServiceLines, filteredClinicalEpisodes and filteredDRGs endpoints | see design | 1.25.1 | 12 |  |  | 12 | Tomek We | April 13, 2021, 3:06 PM |  |  |  |  | PP-981 |  | Sprint 4 | Added to sprint in Sprint 4 |  |  | 0
1.25.4 | Implement searchAllDiagnose endpoint | see design | 1.25.1 | 10 |  |  | 10 | [6 empty] | PP-580 | [5 empty] | 0
1.26 | Location API | Move code and data from existing P2v2 implementation to P2v3 | [11 empty] | PP-542 | [5 empty] | 0
1.26.1 | Move allUSStates endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 | 4 | Manoj | April 2, 2021, 4:02 PM | April 6, 2021, 11:09 AM | 10 | 368 | 78 | PP-543 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/111 | Sprint 4 |  | April 2, 2021, 4:02 PM | April 6, 2021, 11:09 AM | 4
1.26.2 | Move usState endpoint | Copy data to postgres, move django model from P2v2 |  | 2.5 |  | 4 | 4 | Manoj | April 5, 2021, 3:23 PM |  | 2 |  |  | PP-584 |  | Sprint 4 |  | April 5, 2021, 3:23 PM |  | 4
1.26.3 | Move searchUsLocation endpoint | Copy data to postgres, move django model from P2v2 |  | 6 |  | 4 | 4 | Manoj | April 5, 2021, 3:23 PM |  | 2 |  |  | PP-585 |  | Sprint 4 |  | April 5, 2021, 3:23 PM |  | 4
1.26.4 | Move usStateGeoAll endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 | 4 | Manoj | April 1, 2021, 4:58 PM |  | 4 | 60 | 1 | PP-586 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/99 | Sprint 4 |  | April 1, 2021, 4:58 PM |  | 4
1.26.5 | Move usCountyGeoForState endpoint | Copy .json file, make the path configurable | 1.21.1 | 4 |  | 4 | 4 | Manoj | April 1, 2021, 4:59 PM |  | 3 | 60 | 1 | PP-587 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/99 | Sprint 4 |  | April 1, 2021, 4:59 PM |  | 4
1.26.6 | Move usStateGeoSearch | Copy data to postgres, move django model from P2v2 |  | 3.5 |  | 4 | 4 | Manoj | April 5, 2021, 3:24 PM |  | 2 |  |  | PP-588 |  | Sprint 4 |  | April 5, 2021, 3:24 PM |  | 4
1.26.7 | Move usCountyGeoAll endpoint | Copy data to postgres, move django model from P2v2 |  | 2 |  | 4 | 4 | Manoj | April 5, 2021, 3:25 PM |  | 2 |  |  | PP-589 |  | Sprint 4 |  | April 5, 2021, 3:25 PM |  | 4
1.26.8 | Move locationByRadialLocation endpoint | Copy .json file, make the path configurable | 1.21.1 | 8 |  | 4 | 4 | Manoj | April 1, 2021, 5:00 PM |  | 4 | 117 | 0 | PP-590 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/104 | Sprint 4 |  | April 1, 2021, 5:00 PM |  | 4
1.27 | Legend | see design | [11 empty] | PP-982 | [5 empty] | 0
1.27.1 | Implement get_legend_data_statistics | see design, prepare unit tests for all combinations of nodes used in the application | 1.1.12 | 22 |  |  | 22 | [6 empty] | PP-983 | [5 empty] | 0
1.27.2 | Implement is_top_level method | see design |  | 3 |  |  | 3 | [6 empty] | PP-984 | [5 empty] | 0
1.27.3 | Implement get_all_service_line_ids in PandasAnalyticalService |  | 1.1 | 2 |  |  | 2 | [6 empty] | PP-985 | [5 empty] | 0
1.27.4 | Implement get_unique_drgs in PandasAnalyticalService |  | 1.1 | 3 |  |  | 3 | [6 empty] | PP-986 | [5 empty] | 0
1.27.5 | Implement get_top_level_nodes |  | 1.27.3 | 4.5 |  |  | 4.5 | [6 empty] | PP-987 | [5 empty] | 0
1.27.6 | Implement calculate_legend_data method | see design, use is_top_level to avoid unnecessary calculations | 1.27.1 - 1.27.5, 1.29 | 12 |  |  | 12 | [6 empty] | PP-988 | [5 empty] | 0
1.27.7 | Implement format_legend_data method |  |  | 2 |  |  | 2 | [6 empty] | PP-989 | [5 empty] | 0
1.27.8 | Integrate legend data calculation with the caseSummaryCollection endpoint |  | 1.27.6 , 1.27.7 | 5 |  |  | 5 | [6 empty] | PP-990 | [5 empty] | 0
1.28 | Miscellaneous | approx est. ~65h |  |  |  |  | 65 | [6 empty] | PP-991 | [5 empty] | 0
1.28.1 | Distance filter AC/PAC logic | [12 empty] | PP-992 | [5 empty] | 0
1.28.3 | LRU-cache (performance) | [12 empty] | PP-994 | [5 empty] | 0
1.28.4 | Redis cache (performance) | [12 empty] | PP-995 | [5 empty] | 0
1.28.5 | Flexible dataset IDs | [12 empty] | PP-996 | [5 empty] | 0
1.28.6 | Snowflake filter size limitation | [12 empty] | PP-1036
1.29 | Multithreading | see design | [11 empty] | PP-997 | [5 empty] | 0
1.29.1 | Implement AppThreads singleton class | just copy from design | 1.21 | 1 |  |  | 1 | Maciej | April 8, 2021, 9:41 PM | April 8, 2021, 1:28 PM | 0.5 |  |  | PP-998 | - | Sprint 4 | Done, no task in jira |  |  | 1
1.29.2 | Refactor code to use AppThreads singleton | instead of creating ad-hoc ThreadPoolExecutors, modify decompose_packed_nodes, find_child_nodes and possibly other methods | 1.29.1 | 3 |  |  | 3 | Michał | April 14, 2021, 2:56 PM | April 14, 2021, 5:18 PM | 1.5 | 14 | 14 | PP-999 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/133 | Sprint 4 |  |  |  | 3
3 | Report View Management | [12 empty] | PP-356 |  |  | Design not detailed enough to estimate by reviewer/PM |  |  | 0
3.0 | Environment Setup | Setu development environment including DJangoand PGSql |  |  |  |  | 20 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 20 | 147 | 0 | PP-357 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 20
3.1 | Define schema.py | Class that defines graphQL queries, endpoints and object structure. Python file will have definition of following ojects. Developer can refer existing P2BE code at p2backend\ReportView\schema.py file. |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-358 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.2 | Define reportview_api.py | Class that has actual implementation for all end points. Developer can refer p2backend\BigSense\Reportview\reportview_api.py file from existing P2BE code |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-359 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.3 | Define model.py | Class that defines the Entity Relation of report view as per OLTP database(Postgres) |  |  |  |  | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-360 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4 | Implementing Endpoints | This implementation will have a resolve method in schema.py and corresponding method in reportview_api.py file |  |  |  |  | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-361 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.1 | ReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-362 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.2 | ReportViews | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-363 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.3 | SearchReportViews | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-364 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.4 | CreateReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-365 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.4.5 | UpdateReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-366 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:32 PM | March 16, 2021, 6:33 PM | 4
3.4.6 | DeleteReportView | [5 empty] | 4 | Manoj | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4 | 147 | 0 | PP-367 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/20 | Sprint 2 |  | March 5, 2021, 3:31 PM | March 16, 2021, 6:33 PM | 4
3.5 | [BE] Extract user details from Auth0 token |  |  | 8 |  |  | 8 | Manoj, Kamil C | March 25, 2021, 9:52 AM | April 9, 2021, 9:15 AM | 12 | 252 | 5 | PP-516 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/116 | Sprint 4 | Added to sprint in Sprint 3, Postponed from Sprint 3 | March 25, 2021, 9:52 AM | April 9, 2021, 9:15 AM | 8
3.6 | [BE] Modify Report view endpoints to use user details from Auth0 token |  | 3.5 | 12 |  |  | 12 | Manoj | [5 empty] | PP-517 |  |  | Postponed from Sprint 3 |  |  | 0
4 | Integrate analytical endpoints with django | Integrate endpoints with django. To be seen under https://p2v3.ownedoutcomes.com/backend/graphql/ url. List:caseLocationDetails endpoint caseLobCounts endpoint getAvailableYears endpoint getDateTimeStatsForListOfYears endpoint filteredCareUnitTypes endpoint getDatasetsInitialFilters getDateTimesForYear endpoint allDatasets endpoint getLDSDatasetsIDs endpoint |  | 8 |  | 8 | 8 | Tomek We | March 29, 2021, 4:09 PM | March 31, 2021, 3:44 PM | 16 | 88 | 482 | PP-567 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/94 https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/95 | Sprint 3 | Added to sprint in Sprint 3 | March 29, 2021, 4:09 PM | March 31, 2021, 3:44 PM | 8
5 | Implement mock for users endpoint | Implement user query that returns always same user { user { id name emailId __typename } id could be the same as in query: { ReportViews { viewList { owner { id emailId } } } } |  |  |  | 2 | 2 | Manoj | April 1, 2021, 12:40 PM | April 1, 2021, 12:40 PM | 0.5 | 45 | 1 | PP-615 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/101 | Sprint 3 | Added to sprint in Sprint 3 | April 1, 2021, 12:40 PM | April 1, 2021, 12:40 PM | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Bugs
No | Name | Description | Assigned developer | Actual development time |  |  | Commit statistics |  | Jira ID | Commit ID | Comment
|  |  |  | Start time | Finish time | Duration [h] | Insertions | Deletions
1 | Problem with missing DRGs | Problem found during writing unit test. The issue was with type of join of DRG table in already finished implementation. | Maciej, Michał, Ola | March 12, 2021, 8:00 AM | March 15, 2021, 2:10 PM | 20 | 28 | 30 |  | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/28 | Issue delayed finish of group nodes task (1.1.12)
2 | Cannot retrieve stateSummary from caseLocationDetails query | To reproduce: Get into: https://p2v3.ownedoutcomes.com/backend/graphql/ Send query: { caseLocationDetails ( datasets: [{id: "0"}] options: null ) { fipsSummary { id } cbsaSummary { id } stateSummary { id name postalAbbreviation entitySummary { entityType totalCount } } } } Fastest way to reproduce: https://p2v3.ownedoutcomes.com/backend/graphql/#query={ caseLocationDetails ( datasets%3A [{id%3A "0"}] options%3A null ) { fipsSummary { id } cbsaSummary { id } stateSummary { id name postalAbbreviation entitySummary { entityType totalCount } } } } Response: { "errors": [ { "message": "Syntax Error GraphQL (4:14) Unexpected Name \"null\"\n\n3: datasets: [{id: \"0\"}]\n4: options: null\n ^\n5: ) {\n", "locations": [ { "line": 4, "column": 14 } ] } ] } | Michał | April 1, 2021, 9:56 AM | April 1, 2021, 12:00 PM | 1.75 |  |  | PP-616
3 | caseSummaryCollection pagination issue | Problem while sending query similar to one used in rc.bigsense.ai environment. To reproduce: 1. go into https://p2v3.ownedoutcomes.com/backend/graphql/ 2. send query and variables attached: 3. in response you will see only null values | Maciej | April 7, 2021, 12:12 PM | April 7, 2021, 12:12 PM | 5.5 |  |  | PP-622 | https://gitlab-01.itx.pl/p2-project/p2backendv3/-/merge_requests/112
4 | Cannot create a report view | To reproduce: 1. Go to https://p2v3.ownedoutcomes.com/p2/ 2. Click Login button 3. Login: test@test.com Password: 123 4. Go to https://p2v3.ownedoutcomes.com/p2/view-list 5. Try to create a report view. 6. You will receive 400 response from backend (request and response provided below): Request:{"operationName":null,"variables":{"id":"new","name":"245345","isTerrain":false,"orders":[{"isAscending":false,"orderName":"Case_count"}],"labelOption":{"isActive":true,"labels":["Alphabet","Case_count","Star_rating","D90_rr_per_instance"]},"benchmark":{"isEnable":false,"options":[{"aggregationLevel":"National","measure":"D90_rr_per_instance"},{"aggregationLevel":"National","measure":"D90_episode_cost_per_patient"}],"serviceLine":{"id":"","name":""},"clinicalEpisodes":[],"drgs":[],"careUnitType":{"type":""},"metric":{"isAverage":true,"percent":50},"times":{"includedTimes":{"timeRanges":[{"fromTime":{"quarter":"","year":""},"toTime":{"quarter":"","year":""}}]}}},"count":{"casesCount":{"minimumSelectedCount":0,"maximumSelectedCount":0},"entitiesCount":{"minimumSelectedCount":0,"maximumSelectedCount":0}},"threshold":{"isEnabled":false,"details":[]}},"query":"query ($name: String!, $ownerId: ID!, $ownerName: String, $ownerEmail: String, $reportViewType: String, $filters: FilterInputType, $datasets: [DatasetsInputType], $isTerrain: Boolean, $orders: [OrderInputType], $labelOption: LabelOptionInputType, $benchmark: BenchmarkOptionInputType, $count: ReportViewCountInputType) {\n CreateReportView(name: $name, owner: {id: $ownerId, name: $ownerName, emailId: $ownerEmail}, reportViewType: $reportViewType, filters: $filters, datasets: $datasets, isTerrain: $isTerrain, orders: $orders, labelOption: $labelOption, benchmark: $benchmark, count: $count) {\n status\n id\n message\n __typename\n }\n}\n"}Response:{"errors":[{"message":"Variable \"$ownerId\" of required type \"ID!\" was not provided.","locations":[{"line":1,"column":24}]}]} | [6 empty] | PP-1002
5 | Cannot get into report view | To reproduce: 1. Go to https://p2v3.ownedoutcomes.com/p2/ 2. Click Login button 3. Login: test@test.com Password: 123 4. Go to https://p2v3.ownedoutcomes.com/p2/view-list 5. Select any report view 6. You will see a blank screen (problem with respones from backend (below you will see a request and a response): Request:{"operationName":null,"variables":{"datasets":[{"id":null}],"filteredCareUnitTypes":true,"filteredServiceLines":true,"getAvailableYears":true,"getDateTimeStatsForListOfYears":true,"caseLobCounts":true},"query":"query ($datasets: [DatasetsInputType]!, $filteredCareUnitTypes: Boolean, $filteredServiceLines: Boolean, $getAvailableYears: Boolean, $getDateTimeStatsForListOfYears: Boolean, $caseLobCounts: Boolean) {\n getDatasetsInitialFilters(datasets: $datasets, filteredCareUnitTypes: $filteredCareUnitTypes, filteredServiceLines: $filteredServiceLines, getAvailableYears: $getAvailableYears, getDateTimeStatsForListOfYears: $getDateTimeStatsForListOfYears, caseLobCounts: $caseLobCounts) {\n filteredCareUnitTypes {\n id\n name\n numberOfCases\n __typename\n }\n filteredServiceLines {\n id\n name\n numberOfCases\n __typename\n }\n getAvailableYears\n getDateTimeStatsForListOfYears {\n year\n quarterStats {\n quarter\n caseCount\n entityCount\n __typename\n }\n __typename\n }\n caseLobCounts {\n id\n name\n numberOfCases\n __typename\n }\n __typename\n }\n}\n"}Response:{"errors":[{"message":"int() argument must be a string, a bytes-like object or a number, not 'NoneType'","locations":[{"line":2,"column":3}],"path":["getDatasetsInitialFilters"]}],"data":{"getDatasetsInitialFilters":null}} | Tomek We | [5 empty] | PP-1003

## Planned availability
Date | Devs | Hrs | Cummulative
2021-04-12 | 7 | 42 | 42 | Sprint 4
2021-04-13 | 7 | 42 | 84 | Sprint 4
2021-04-14 | 7 | 42 | 126 | Sprint 4
2021-04-15 | 7 | 42 | 168 | Sprint 4
2021-04-16 | 7 | 42 | 210 | Sprint 4
2021-04-17 | 0 | 0 | 210
2021-04-18 | 0 | 0 | 210
2021-04-19 | 8 | 48 | 258 | Sprint 5
2021-04-20 | 8 | 48 | 306 | Sprint 5
2021-04-21 | 8 | 48 | 354 | Sprint 5
2021-04-22 | 8 | 48 | 402 | Sprint 5 | ds | group | be
2021-04-23 | 8 | 48 | 450 | Sprint 5 | 114 | 622 | 1979 | 2715
2021-04-24 | 0 | 0 | 450 |  | 114 | 271 | 1077.5 | 1462.5
2021-04-25 | 0 | 0 | 450 |  | 125.002 | 174.25 | 1012.89 | 1312.142
2021-04-26 | 8 | 48 | 498 | Sprint 5 | 0 | 351 | 901.5 | 1252.5
2021-04-27 | 8 | 48 | 546 | Sprint 5
2021-04-28 | 8 | 48 | 594 | Sprint 5 | 100 | 43.5691 | 54.4467 | 53.8674
2021-04-29 | 8 | 48 | 642 | Sprint 5 | 109.6509 | 64.2989 | 94.0037 | 89.7191
2021-04-30 | 8 | 48 | 690 | Sprint 5
2021-05-01 | 0 | 0 | 690
2021-05-02 | 0 | 0 | 690
2021-05-03 | 0 | 0 | 690 | Sprint 5
2021-05-04 | 8 | 48 | 738 | Sprint 6
2021-05-05 | 8 | 48 | 786 | Sprint 6
2021-05-06 | 8 | 48 | 834 | Sprint 6
2021-05-07 | 8 | 48 | 882 | Sprint 6
2021-05-08 | 0 | 0 | 882
2021-05-09 | 0 | 0 | 882
2021-05-10 | 8 | 48 | 930 | Sprint 6
2021-05-11 | 8 | 48 | 978 | Sprint 6
2021-05-12 | 8 | 48 | 1026 | Sprint 6
2021-05-13 | 8 | 48 | 1074 | Sprint 6
2021-05-14 | 8 | 48 | 1122 | Sprint 6
2021-05-15 | 0 | 0 | 1122
2021-05-16 | 0 | 0 | 1122
2021-05-17 | 6.5 | 39 | 1161 | Sprint 7
2021-05-18 | 6.5 | 39 | 1200 | Sprint 7
2021-05-19 | 6.5 | 39 | 1239 | Sprint 7
2021-05-20 | 6.5 | 39 | 1278 | Sprint 7
2021-05-21 | 6.5 | 39 | 1317 | Sprint 7
2021-05-22 | 0 | 0 | 1317
2021-05-23 | 0 | 0 | 1317
2021-05-24 | 6.5 | 39 | 1356 | Sprint 7
2021-05-25 | 6.5 | 39 | 1395 | Sprint 7
2021-05-26 | 6.5 | 39 | 1434 | Sprint 7
2021-05-27 | 6.5 | 39 | 1473 | Sprint 7
2021-05-28 | 6.5 | 39 | 1512 | Sprint 7
2021-05-29 | 0 | 0 | 1512
2021-05-30 | 0 | 0 | 1512
2021-05-31 | 6.5 | 39 | 1551
2021-06-01 | 6.5 | 39 | 1590
2021-06-02 | 6.5 | 39 | 1629
2021-06-03 | 6.5 | 39 | 1668
2021-06-04 | 6.5 | 39 | 1707
2021-06-05 | 6.5 | 39 | 1746